## Sheet1
System Name | Pet Shop and Boutique System
Members:
Canasa, Jared Chester
Seville, Vince Kyrie
Sevenial, Charles William
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1) Signup/Sign-in Form | Sevenial | 2024-09-26 | 2024-10-26 | Done
-Registration | Sevenial | 2024-09-26 | 2024-10-26 | Done
-Login | Sevenial | 2024-09-26 | 2024-10-26 | Done
2)Inventory | Sevenial | 2024-10-13 |  | Done
-Edit Products | Sevenial | 2024-10-13 |  | Done
-DeleteProducts | Sevenial | 2024-10-13 |  | Done
-Layout | Sevenial | 2024-10-13 |  | Done
-Design | Sevenial | 2024-10-13 |  | Done
2)Home Page | Canasa | 2024-09-27 | 2024-10-26 | Done
-Layout | Canasa | 2024-09-27 | 2024-10-26 | Done
-Design | Canasa | 2024-09-27 | 2024-10-26 | Done
3)Product Details | Canasa | 2024-09-28 | 2024-10-26 | Done
-Design | Canasa | 2024-10-14 | 2024-10-26 | Done
-Functionality | Canasa | 2024-10-14 | 2024-10-26 | Done
4)Product Filtering | Seville | 2024-10-14 |  | Done
-Sort | Seville | 2024-10-14 |  | Done
-Layout | Seville | 2024-10-14 |  | Done
-Design | Seville | 2024-10-14 |  | Done
5)Product Reviews | Seville | 2024-10-27 |  | In-Progress
-Layout | Seville | 2024-10-27 |  | In-Progress
-Design | Seville | 2024-10-27 |  | In-Progress
-Database | Seville | 2024-10-27 |  | In-Progress
6)Appointment Tab | Sevenial | 2024-11-02 |  | Done
-Layout | Sevenial | 2024-11-02 |  | Done
-Design | Sevenial | 2024-11-02 |  | Done
7)Order Placement | Canasa | 2024-10-17 |  | Done
-Layout | Canasa | 2024-10-17 |  | Done
-Design | Canasa | 2024-10-17 |  | Done
-Database | Canasa | 2024-10-17 |  | Done
8)Landing Page | Sevenial | 2024-10-01 | 2024-10-27 | Done
-Layout | Sevenial | 2024-10-01 | 2024-10-27 | Done
-Design | Sevenial | 2024-10-01 | 2024-10-27 | Done
8)Database | Canasa | Week 5 |  | Done
-Structure | Canasa | Week 5 |  | Done